## Problem 3
Adrian Harris
Professor Blau | Task | Description | Time | ES | EF | LS | LF | SLACK | CRITICAL
OPR 3450 | Start |  | 0 | 0 | 0 | 0 | 0 | 0 | Yes
2019-05-26 | A | Buy the cheese | 30 | 0 | 30 | 0 | 30 | 0 | Yes
Final | B | Slice the cheese | 5 | 30 | 35 | 30 | 35 | 0 | Yes
Problem Three | C | Beat 2 eggs | 2 | 0 | 2 | 30 | 32 | 30 | No
| D | Mix eggs and cheese | 3 | 2 | 5 | 32 | 35 | 30 | No
| E | Cut up onions and mushrooms | 7 | 0 | 7 | 3 | 10 | 3 | No
| F | Cook the tomate sauce | 25 | 7 | 32 | 10 | 35 | 3 | No
| G | Boil large quantity of water | 15 | 0 | 15 | 8 | 23 | 8 | No
| H | Boil the lasagna noodles | 10 | 15 | 25 | 23 | 33 | 8 | No
| I | Drain the lasagna | 2 | 25 | 27 | 33 | 35 | 8 | No
| J | Assemble all the ingredients | 10 | 35 | 45 | 35 | 45 | 0 | Yes
| K | Preheat oven | 15 | 0 | 15 | 30 | 45 | 30 | No
| L | Bake the lasagna | 30 | 45 | 75 | 45 | 75 | 0 | Yes

## Problem 4 revised
Adrian Harris |  | Cumulative | x | y
Professor Blau |  | 0 | 0 | 0 | Sleeps | 0.4
OPR 3450 |  | 0.4 | 1 | 0 | east | 0.15
2019-05-26 |  | 0.55 | 1 | 0 | north | 0.15 | Std | 2.2172
Problem Four |  | 0.7 | -1 | 0 | west | 0.15
|  | 0.85 | 0 | -1 | south | 0.15
|  | Steps | x | y | random |  |  | x | y | sum | Possible ways for 2 blocks or less
|  | 1 | 1 | 0 |  |  | A. Average blocks walked | 2.315 | 1.208 | 3.523 | 0 | 2 | 0
|  | 2 | 1 | 0 | 0.055719 | [5 empty] | 0 | -2 | 34
|  | 3 | 0 | 0 | 0.79441 |  | B. Average blocks from store | 2.075 | -1.208 | 0.867 | -2 | 0 | 8
|  | 4 | -1 | 0 | 0.84948 | [5 empty] | 2 | 0 | 58
|  | 5 | -1 | 0 | 0.28636 |  | C. (P) two blocks or less | 0.309 |  |  | 1 | 1 | 0
|  | 6 | -2 | 0 | 0.78413 | [5 empty] | 1 | -1 | 56
|  | 7 | -2 | 0 | 0.34938 |  | D. Upper bound | 0.44642 |  |  | -1 | 1 | 0
|  | 8 | -3 | 0 | 0.75351 |  | D. Lower bound | 0.17158 |  |  | -1 | -1 | 25
|  | 9 | -4 | 0 | 0.71271 | [5 empty] | 0 | 1 | 0
[11 empty] | 0 | -1 | 48
[11 empty] | -1 | 0 | 10
|  | x | y |  | x(abs) | y(abs) |  |  |  |  | 1 | 0 | 49
|  | -4 | 0 | [7 empty] | 0 | 0 | 21
| Trial 1 | 1 | -1 |  | 1 | 1 | [6 empty] | 309
| Trial 2 | 0 | -2 |  | 0 | 2
| Trial 3 | 0 | -2 |  | 0 | 2
| Trial 4 | 2 | 0 |  | 2 | 0
| Trial 5 | 5 | -1 |  | 5 | 1
| Trial 6 | 2 | -3 |  | 2 | 3
| Trial 7 | 3 | 0 |  | 3 | 0
| Trial 8 | 2 | -1 |  | 2 | 1
| Trial 9 | 5 | -1 |  | 5 | 1
| Trial 10 | 2 | 0 |  | 2 | 0
| Trial 11 | 0 | -1 |  | 0 | 1
| Trial 12 | 5 | -2 |  | 5 | 2
| Trial 13 | 0 | -2 |  | 0 | 2
| Trial 14 | 1 | -1 |  | 1 | 1
| Trial 15 | 3 | -4 |  | 3 | 4
| Trial 16 | 5 | -1 |  | 5 | 1
| Trial 17 | 1 | 0 |  | 1 | 0
| Trial 18 | 4 | -2 |  | 4 | 2
| Trial 19 | 2 | -1 |  | 2 | 1
| Trial 20 | -1 | 0 |  | 1 | 0
| Trial 21 | 4 | 0 |  | 4 | 0
| Trial 22 | 2 | -2 |  | 2 | 2
| Trial 23 | 3 | 0 |  | 3 | 0
| Trial 24 | 3 | 0 |  | 3 | 0
| Trial 25 | 1 | 0 |  | 1 | 0
| Trial 26 | 2 | -3 |  | 2 | 3
| Trial 27 | 1 | 0 |  | 1 | 0
| Trial 28 | 0 | -1 |  | 0 | 1
| Trial 29 | -1 | 0 |  | 1 | 0
| Trial 30 | 3 | -1 |  | 3 | 1
| Trial 31 | 0 | 0 |  | 0 | 0
| Trial 32 | 2 | -4 |  | 2 | 4
| Trial 33 | 3 | -3 |  | 3 | 3
| Trial 34 | -1 | -2 |  | 1 | 2
| Trial 35 | 3 | -1 |  | 3 | 1
| Trial 36 | 0 | -1 |  | 0 | 1
| Trial 37 | 2 | -2 |  | 2 | 2
| Trial 38 | 3 | 0 |  | 3 | 0
| Trial 39 | 2 | -1 |  | 2 | 1
| Trial 40 | 2 | -1 |  | 2 | 1
| Trial 41 | 3 | -1 |  | 3 | 1
| Trial 42 | 4 | -1 |  | 4 | 1
| Trial 43 | 5 | -3 |  | 5 | 3
| Trial 44 | 1 | -1 |  | 1 | 1
| Trial 45 | 1 | -2 |  | 1 | 2
| Trial 46 | 6 | -2 |  | 6 | 2
| Trial 47 | 3 | -2 |  | 3 | 2
| Trial 48 | 2 | 0 |  | 2 | 0
| Trial 49 | -1 | -1 |  | 1 | 1
| Trial 50 | 1 | -1 |  | 1 | 1
| Trial 51 | 2 | -3 |  | 2 | 3
| Trial 52 | 0 | -2 |  | 0 | 2
| Trial 53 | 1 | -4 |  | 1 | 4
| Trial 54 | -1 | -1 |  | 1 | 1
| Trial 55 | 1 | 0 |  | 1 | 0
| Trial 56 | 0 | -1 |  | 0 | 1
| Trial 57 | 4 | -2 |  | 4 | 2
| Trial 58 | 1 | -2 |  | 1 | 2
| Trial 59 | 2 | -1 |  | 2 | 1
| Trial 60 | 5 | -1 |  | 5 | 1
| Trial 61 | 1 | -2 |  | 1 | 2
| Trial 62 | 0 | -3 |  | 0 | 3
| Trial 63 | 1 | -2 |  | 1 | 2
| Trial 64 | 2 | 0 |  | 2 | 0
| Trial 65 | 6 | -1 |  | 6 | 1
| Trial 66 | 0 | -1 |  | 0 | 1
| Trial 67 | 2 | -1 |  | 2 | 1
| Trial 68 | 2 | -2 |  | 2 | 2
| Trial 69 | 4 | -2 |  | 4 | 2
| Trial 70 | 2 | -2 |  | 2 | 2
| Trial 71 | -3 | -1 |  | 3 | 1
| Trial 72 | 6 | 0 |  | 6 | 0
| Trial 73 | 1 | -1 |  | 1 | 1
| Trial 74 | 1 | 0 |  | 1 | 0
| Trial 75 | 0 | -2 |  | 0 | 2
| Trial 76 | -1 | -2 |  | 1 | 2
| Trial 77 | 1 | -3 |  | 1 | 3
| Trial 78 | 2 | -2 |  | 2 | 2
| Trial 79 | 2 | 0 |  | 2 | 0
| Trial 80 | 4 | 0 |  | 4 | 0
| Trial 81 | 3 | -1 |  | 3 | 1
| Trial 82 | 2 | -2 |  | 2 | 2
| Trial 83 | 2 | 0 |  | 2 | 0
| Trial 84 | 1 | -2 |  | 1 | 2
| Trial 85 | 2 | 0 |  | 2 | 0
| Trial 86 | -2 | -1 |  | 2 | 1
| Trial 87 | 6 | -1 |  | 6 | 1
| Trial 88 | 1 | 0 |  | 1 | 0
| Trial 89 | 2 | -4 |  | 2 | 4
| Trial 90 | 5 | 0 |  | 5 | 0
| Trial 91 | 1 | 0 |  | 1 | 0
| Trial 92 | 3 | 0 |  | 3 | 0
| Trial 93 | 1 | 0 |  | 1 | 0
| Trial 94 | -1 | -3 |  | 1 | 3
| Trial 95 | 2 | -1 |  | 2 | 1
| Trial 96 | 1 | -3 |  | 1 | 3
| Trial 97 | 3 | -1 |  | 3 | 1
| Trial 98 | 2 | 0 |  | 2 | 0
| Trial 99 | -2 | -2 |  | 2 | 2
| Trial 100 | -2 | 0 |  | 2 | 0
| Trial 101 | 3 | -2 |  | 3 | 2
| Trial 102 | 2 | -3 |  | 2 | 3
| Trial 103 | 3 | -2 |  | 3 | 2
| Trial 104 | 2 | -2 |  | 2 | 2
| Trial 105 | 3 | -1 |  | 3 | 1
| Trial 106 | 2 | 0 |  | 2 | 0
| Trial 107 | 2 | -3 |  | 2 | 3
| Trial 108 | 4 | 0 |  | 4 | 0
| Trial 109 | -1 | -1 |  | 1 | 1
| Trial 110 | 1 | -3 |  | 1 | 3
| Trial 111 | 2 | -1 |  | 2 | 1
| Trial 112 | 0 | 0 |  | 0 | 0
| Trial 113 | 5 | -1 |  | 5 | 1
| Trial 114 | 3 | -1 |  | 3 | 1
| Trial 115 | 5 | -2 |  | 5 | 2
| Trial 116 | 0 | -1 |  | 0 | 1
| Trial 117 | 3 | -1 |  | 3 | 1
| Trial 118 | 1 | -2 |  | 1 | 2
| Trial 119 | 2 | 0 |  | 2 | 0
| Trial 120 | 2 | 0 |  | 2 | 0
| Trial 121 | 0 | -1 |  | 0 | 1
| Trial 122 | 0 | -3 |  | 0 | 3
| Trial 123 | 3 | -3 |  | 3 | 3
| Trial 124 | 6 | -1 |  | 6 | 1
| Trial 125 | 2 | -2 |  | 2 | 2
| Trial 126 | 3 | -1 |  | 3 | 1
| Trial 127 | 4 | -1 |  | 4 | 1
| Trial 128 | 3 | 0 |  | 3 | 0
| Trial 129 | 0 | -2 |  | 0 | 2
| Trial 130 | 3 | -1 |  | 3 | 1
| Trial 131 | -3 | 0 |  | 3 | 0
| Trial 132 | 1 | -3 |  | 1 | 3
| Trial 133 | 2 | -2 |  | 2 | 2
| Trial 134 | 3 | -2 |  | 3 | 2
| Trial 135 | 5 | 0 |  | 5 | 0
| Trial 136 | 3 | 0 |  | 3 | 0
| Trial 137 | 3 | -1 |  | 3 | 1
| Trial 138 | 4 | 0 |  | 4 | 0
| Trial 139 | 0 | -1 |  | 0 | 1
| Trial 140 | 2 | -1 |  | 2 | 1
| Trial 141 | 2 | -1 |  | 2 | 1
| Trial 142 | -1 | -1 |  | 1 | 1
| Trial 143 | 1 | 0 |  | 1 | 0
| Trial 144 | 3 | -2 |  | 3 | 2
| Trial 145 | -1 | -1 |  | 1 | 1
| Trial 146 | 2 | 0 |  | 2 | 0
| Trial 147 | 5 | -1 |  | 5 | 1
| Trial 148 | 4 | -3 |  | 4 | 3
| Trial 149 | 2 | -1 |  | 2 | 1
| Trial 150 | 1 | -1 |  | 1 | 1
| Trial 151 | 3 | -1 |  | 3 | 1
| Trial 152 | 5 | -2 |  | 5 | 2
| Trial 153 | -1 | -2 |  | 1 | 2
| Trial 154 | 2 | -2 |  | 2 | 2
| Trial 155 | 1 | -1 |  | 1 | 1
| Trial 156 | 2 | -3 |  | 2 | 3
| Trial 157 | 3 | -1 |  | 3 | 1
| Trial 158 | 4 | -1 |  | 4 | 1
| Trial 159 | 0 | -1 |  | 0 | 1
| Trial 160 | 3 | -1 |  | 3 | 1
| Trial 161 | 1 | -1 |  | 1 | 1
| Trial 162 | 4 | -1 |  | 4 | 1
| Trial 163 | 4 | 0 |  | 4 | 0
| Trial 164 | 1 | 0 |  | 1 | 0
| Trial 165 | 4 | -3 |  | 4 | 3
| Trial 166 | -1 | -1 |  | 1 | 1
| Trial 167 | 6 | -1 |  | 6 | 1
| Trial 168 | 3 | -3 |  | 3 | 3
| Trial 169 | 4 | -1 |  | 4 | 1
| Trial 170 | 0 | -1 |  | 0 | 1
| Trial 171 | 1 | -2 |  | 1 | 2
| Trial 172 | 2 | -2 |  | 2 | 2
| Trial 173 | -2 | -2 |  | 2 | 2
| Trial 174 | 5 | -2 |  | 5 | 2
| Trial 175 | 0 | -1 |  | 0 | 1
| Trial 176 | 3 | -1 |  | 3 | 1
| Trial 177 | 2 | 0 |  | 2 | 0
| Trial 178 | 1 | -1 |  | 1 | 1
| Trial 179 | 1 | 0 |  | 1 | 0
| Trial 180 | 1 | -1 |  | 1 | 1
| Trial 181 | 1 | -2 |  | 1 | 2
| Trial 182 | 2 | -2 |  | 2 | 2
| Trial 183 | 3 | -1 |  | 3 | 1
| Trial 184 | 0 | -1 |  | 0 | 1
| Trial 185 | 6 | -1 |  | 6 | 1
| Trial 186 | 0 | -1 |  | 0 | 1
| Trial 187 | 0 | -2 |  | 0 | 2
| Trial 188 | 3 | -3 |  | 3 | 3
| Trial 189 | 0 | -1 |  | 0 | 1
| Trial 190 | 4 | -1 |  | 4 | 1
| Trial 191 | 1 | 0 |  | 1 | 0
| Trial 192 | 0 | 0 |  | 0 | 0
| Trial 193 | 2 | -2 |  | 2 | 2
| Trial 194 | 3 | 0 |  | 3 | 0
| Trial 195 | 0 | 0 |  | 0 | 0
| Trial 196 | 3 | -1 |  | 3 | 1
| Trial 197 | 1 | 0 |  | 1 | 0
| Trial 198 | 1 | 0 |  | 1 | 0
| Trial 199 | 4 | 0 |  | 4 | 0
| Trial 200 | 1 | -1 |  | 1 | 1
| Trial 201 | 0 | -2 |  | 0 | 2
| Trial 202 | 7 | -1 |  | 7 | 1
| Trial 203 | 2 | -1 |  | 2 | 1
| Trial 204 | 2 | -1 |  | 2 | 1
| Trial 205 | -1 | -2 |  | 1 | 2
| Trial 206 | 4 | -2 |  | 4 | 2
| Trial 207 | 2 | -2 |  | 2 | 2
| Trial 208 | 1 | -1 |  | 1 | 1
| Trial 209 | 1 | 0 |  | 1 | 0
| Trial 210 | 0 | -1 |  | 0 | 1
| Trial 211 | 1 | -1 |  | 1 | 1
| Trial 212 | 6 | 0 |  | 6 | 0
| Trial 213 | 3 | 0 |  | 3 | 0
| Trial 214 | 3 | -1 |  | 3 | 1
| Trial 215 | 1 | 0 |  | 1 | 0
| Trial 216 | 1 | 0 |  | 1 | 0
| Trial 217 | 3 | -1 |  | 3 | 1
| Trial 218 | 1 | -1 |  | 1 | 1
| Trial 219 | 1 | 0 |  | 1 | 0
| Trial 220 | 4 | -1 |  | 4 | 1
| Trial 221 | 2 | 0 |  | 2 | 0
| Trial 222 | 0 | -4 |  | 0 | 4
| Trial 223 | 3 | -2 |  | 3 | 2
| Trial 224 | 3 | -1 |  | 3 | 1
| Trial 225 | 1 | -2 |  | 1 | 2
| Trial 226 | 1 | -1 |  | 1 | 1
| Trial 227 | 5 | 0 |  | 5 | 0
| Trial 228 | 0 | -2 |  | 0 | 2
| Trial 229 | 3 | -2 |  | 3 | 2
| Trial 230 | 2 | -2 |  | 2 | 2
| Trial 231 | 2 | 0 |  | 2 | 0
| Trial 232 | 1 | -3 |  | 1 | 3
| Trial 233 | 4 | -2 |  | 4 | 2
| Trial 234 | 3 | 0 |  | 3 | 0
| Trial 235 | 4 | -2 |  | 4 | 2
| Trial 236 | 5 | -1 |  | 5 | 1
| Trial 237 | 1 | -2 |  | 1 | 2
| Trial 238 | 5 | -1 |  | 5 | 1
| Trial 239 | 2 | -1 |  | 2 | 1
| Trial 240 | 2 | 0 |  | 2 | 0
| Trial 241 | 3 | 0 |  | 3 | 0
| Trial 242 | 1 | 0 |  | 1 | 0
| Trial 243 | -1 | -1 |  | 1 | 1
| Trial 244 | 3 | -1 |  | 3 | 1
| Trial 245 | 2 | -1 |  | 2 | 1
| Trial 246 | 1 | 0 |  | 1 | 0
| Trial 247 | -1 | -3 |  | 1 | 3
| Trial 248 | 2 | -2 |  | 2 | 2
| Trial 249 | 2 | -3 |  | 2 | 3
| Trial 250 | 3 | -3 |  | 3 | 3
| Trial 251 | 2 | -1 |  | 2 | 1
| Trial 252 | 0 | -1 |  | 0 | 1
| Trial 253 | 4 | 0 |  | 4 | 0
| Trial 254 | 1 | -2 |  | 1 | 2
| Trial 255 | 2 | 0 |  | 2 | 0
| Trial 256 | 1 | -1 |  | 1 | 1
| Trial 257 | 2 | -2 |  | 2 | 2
| Trial 258 | 3 | -1 |  | 3 | 1
| Trial 259 | 2 | -2 |  | 2 | 2
| Trial 260 | 2 | -3 |  | 2 | 3
| Trial 261 | 1 | 0 |  | 1 | 0
| Trial 262 | -2 | -1 |  | 2 | 1
| Trial 263 | 2 | -1 |  | 2 | 1
| Trial 264 | 4 | -3 |  | 4 | 3
| Trial 265 | 2 | -1 |  | 2 | 1
| Trial 266 | 0 | -1 |  | 0 | 1
| Trial 267 | 3 | -2 |  | 3 | 2
| Trial 268 | 0 | -1 |  | 0 | 1
| Trial 269 | 4 | -1 |  | 4 | 1
| Trial 270 | 0 | -1 |  | 0 | 1
| Trial 271 | -1 | -1 |  | 1 | 1
| Trial 272 | 2 | -2 |  | 2 | 2
| Trial 273 | 1 | -1 |  | 1 | 1
| Trial 274 | 1 | -1 |  | 1 | 1
| Trial 275 | 1 | -3 |  | 1 | 3
| Trial 276 | 2 | -1 |  | 2 | 1
| Trial 277 | 3 | -1 |  | 3 | 1
| Trial 278 | 2 | -1 |  | 2 | 1
| Trial 279 | 2 | -3 |  | 2 | 3
| Trial 280 | 4 | -1 |  | 4 | 1
| Trial 281 | 1 | -1 |  | 1 | 1
| Trial 282 | 3 | -2 |  | 3 | 2
| Trial 283 | 2 | -1 |  | 2 | 1
| Trial 284 | 3 | -2 |  | 3 | 2
| Trial 285 | -2 | 0 |  | 2 | 0
| Trial 286 | 2 | -1 |  | 2 | 1
| Trial 287 | 2 | -1 |  | 2 | 1
| Trial 288 | 1 | -1 |  | 1 | 1
| Trial 289 | -1 | -3 |  | 1 | 3
| Trial 290 | 1 | -2 |  | 1 | 2
| Trial 291 | 2 | -3 |  | 2 | 3
| Trial 292 | 1 | -1 |  | 1 | 1
| Trial 293 | 5 | 0 |  | 5 | 0
| Trial 294 | 3 | -2 |  | 3 | 2
| Trial 295 | 1 | -4 |  | 1 | 4
| Trial 296 | 3 | -1 |  | 3 | 1
| Trial 297 | 1 | -1 |  | 1 | 1
| Trial 298 | 5 | 0 |  | 5 | 0
| Trial 299 | 3 | -2 |  | 3 | 2
| Trial 300 | 3 | -1 |  | 3 | 1
| Trial 301 | 4 | 0 |  | 4 | 0
| Trial 302 | 0 | -1 |  | 0 | 1
| Trial 303 | 5 | -1 |  | 5 | 1
| Trial 304 | -1 | -1 |  | 1 | 1
| Trial 305 | 0 | -1 |  | 0 | 1
| Trial 306 | 4 | -1 |  | 4 | 1
| Trial 307 | 0 | 0 |  | 0 | 0
| Trial 308 | -1 | 0 |  | 1 | 0
| Trial 309 | 3 | -2 |  | 3 | 2
| Trial 310 | 1 | -2 |  | 1 | 2
| Trial 311 | -1 | -1 |  | 1 | 1
| Trial 312 | 3 | 0 |  | 3 | 0
| Trial 313 | 6 | 0 |  | 6 | 0
| Trial 314 | 0 | -3 |  | 0 | 3
| Trial 315 | 2 | -2 |  | 2 | 2
| Trial 316 | 2 | -1 |  | 2 | 1
| Trial 317 | 3 | -2 |  | 3 | 2
| Trial 318 | 2 | -2 |  | 2 | 2
| Trial 319 | 5 | 0 |  | 5 | 0
| Trial 320 | 6 | -3 |  | 6 | 3
| Trial 321 | 1 | -1 |  | 1 | 1
| Trial 322 | 0 | -1 |  | 0 | 1
| Trial 323 | 0 | -1 |  | 0 | 1
| Trial 324 | 2 | 0 |  | 2 | 0
| Trial 325 | 3 | 0 |  | 3 | 0
| Trial 326 | -2 | -1 |  | 2 | 1
| Trial 327 | 1 | -1 |  | 1 | 1
| Trial 328 | 2 | 0 |  | 2 | 0
| Trial 329 | 3 | -1 |  | 3 | 1
| Trial 330 | 3 | 0 |  | 3 | 0
| Trial 331 | 3 | -3 |  | 3 | 3
| Trial 332 | 6 | 0 |  | 6 | 0
| Trial 333 | 4 | -1 |  | 4 | 1
| Trial 334 | 2 | -1 |  | 2 | 1
| Trial 335 | 3 | -2 |  | 3 | 2
| Trial 336 | 5 | 0 |  | 5 | 0
| Trial 337 | 0 | -1 |  | 0 | 1
| Trial 338 | 0 | 0 |  | 0 | 0
| Trial 339 | 2 | -2 |  | 2 | 2
| Trial 340 | 1 | -1 |  | 1 | 1
| Trial 341 | 1 | -1 |  | 1 | 1
| Trial 342 | 1 | -1 |  | 1 | 1
| Trial 343 | 2 | 0 |  | 2 | 0
| Trial 344 | 1 | 0 |  | 1 | 0
| Trial 345 | 5 | -2 |  | 5 | 2
| Trial 346 | 4 | -3 |  | 4 | 3
| Trial 347 | 7 | 0 |  | 7 | 0
| Trial 348 | 4 | -1 |  | 4 | 1
| Trial 349 | 2 | 0 |  | 2 | 0
| Trial 350 | 0 | -2 |  | 0 | 2
| Trial 351 | 3 | -2 |  | 3 | 2
| Trial 352 | 3 | 0 |  | 3 | 0
| Trial 353 | 4 | -1 |  | 4 | 1
| Trial 354 | 3 | -2 |  | 3 | 2
| Trial 355 | 2 | -1 |  | 2 | 1
| Trial 356 | 2 | -2 |  | 2 | 2
| Trial 357 | 3 | 0 |  | 3 | 0
| Trial 358 | 3 | -2 |  | 3 | 2
| Trial 359 | 5 | -1 |  | 5 | 1
| Trial 360 | 2 | -1 |  | 2 | 1
| Trial 361 | 0 | -2 |  | 0 | 2
| Trial 362 | 1 | -2 |  | 1 | 2
| Trial 363 | 5 | -1 |  | 5 | 1
| Trial 364 | 3 | -2 |  | 3 | 2
| Trial 365 | 2 | -1 |  | 2 | 1
| Trial 366 | -2 | -3 |  | 2 | 3
| Trial 367 | 6 | 0 |  | 6 | 0
| Trial 368 | 3 | -1 |  | 3 | 1
| Trial 369 | 2 | 0 |  | 2 | 0
| Trial 370 | 4 | -1 |  | 4 | 1
| Trial 371 | 1 | -1 |  | 1 | 1
| Trial 372 | -1 | -2 |  | 1 | 2
| Trial 373 | 1 | -3 |  | 1 | 3
| Trial 374 | 2 | -4 |  | 2 | 4
| Trial 375 | 3 | -1 |  | 3 | 1
| Trial 376 | 1 | -4 |  | 1 | 4
| Trial 377 | 2 | -1 |  | 2 | 1
| Trial 378 | 0 | -1 |  | 0 | 1
| Trial 379 | 4 | -2 |  | 4 | 2
| Trial 380 | 1 | -1 |  | 1 | 1
| Trial 381 | 2 | 0 |  | 2 | 0
| Trial 382 | -1 | -2 |  | 1 | 2
| Trial 383 | 2 | -1 |  | 2 | 1
| Trial 384 | 1 | -1 |  | 1 | 1
| Trial 385 | 5 | -2 |  | 5 | 2
| Trial 386 | 2 | -2 |  | 2 | 2
| Trial 387 | 2 | -1 |  | 2 | 1
| Trial 388 | 5 | 0 |  | 5 | 0
| Trial 389 | 3 | 0 |  | 3 | 0
| Trial 390 | 1 | -1 |  | 1 | 1
| Trial 391 | 3 | -2 |  | 3 | 2
| Trial 392 | 2 | -2 |  | 2 | 2
| Trial 393 | 5 | 0 |  | 5 | 0
| Trial 394 | 3 | 0 |  | 3 | 0
| Trial 395 | -2 | 0 |  | 2 | 0
| Trial 396 | 0 | -1 |  | 0 | 1
| Trial 397 | 2 | -1 |  | 2 | 1
| Trial 398 | 3 | -1 |  | 3 | 1
| Trial 399 | 0 | -1 |  | 0 | 1
| Trial 400 | 3 | -1 |  | 3 | 1
| Trial 401 | 4 | -2 |  | 4 | 2
| Trial 402 | 2 | 0 |  | 2 | 0
| Trial 403 | 4 | 0 |  | 4 | 0
| Trial 404 | 4 | -3 |  | 4 | 3
| Trial 405 | 1 | -2 |  | 1 | 2
| Trial 406 | 0 | -2 |  | 0 | 2
| Trial 407 | 2 | -1 |  | 2 | 1
| Trial 408 | 0 | -3 |  | 0 | 3
| Trial 409 | 3 | -3 |  | 3 | 3
| Trial 410 | 1 | -1 |  | 1 | 1
| Trial 411 | -1 | -1 |  | 1 | 1
| Trial 412 | 4 | -1 |  | 4 | 1
| Trial 413 | 3 | -2 |  | 3 | 2
| Trial 414 | -1 | -1 |  | 1 | 1
| Trial 415 | -1 | -1 |  | 1 | 1
| Trial 416 | 4 | 0 |  | 4 | 0
| Trial 417 | 5 | -1 |  | 5 | 1
| Trial 418 | 2 | -2 |  | 2 | 2
| Trial 419 | 2 | 0 |  | 2 | 0
| Trial 420 | 6 | -1 |  | 6 | 1
| Trial 421 | 1 | 0 |  | 1 | 0
| Trial 422 | 4 | -1 |  | 4 | 1
| Trial 423 | 5 | 0 |  | 5 | 0
| Trial 424 | 0 | -2 |  | 0 | 2
| Trial 425 | -1 | -1 |  | 1 | 1
| Trial 426 | 5 | -2 |  | 5 | 2
| Trial 427 | 0 | -2 |  | 0 | 2
| Trial 428 | 2 | -2 |  | 2 | 2
| Trial 429 | 0 | -2 |  | 0 | 2
| Trial 430 | 1 | -2 |  | 1 | 2
| Trial 431 | 2 | -1 |  | 2 | 1
| Trial 432 | 3 | -1 |  | 3 | 1
| Trial 433 | 0 | -2 |  | 0 | 2
| Trial 434 | 3 | -1 |  | 3 | 1
| Trial 435 | 2 | -2 |  | 2 | 2
| Trial 436 | 3 | 0 |  | 3 | 0
| Trial 437 | 2 | -3 |  | 2 | 3
| Trial 438 | 0 | -2 |  | 0 | 2
| Trial 439 | 2 | -2 |  | 2 | 2
| Trial 440 | 1 | -1 |  | 1 | 1
| Trial 441 | 2 | -1 |  | 2 | 1
| Trial 442 | 3 | -2 |  | 3 | 2
| Trial 443 | -1 | -3 |  | 1 | 3
| Trial 444 | 4 | -1 |  | 4 | 1
| Trial 445 | 2 | -2 |  | 2 | 2
| Trial 446 | -1 | -1 |  | 1 | 1
| Trial 447 | 4 | 0 |  | 4 | 0
| Trial 448 | 1 | -1 |  | 1 | 1
| Trial 449 | -2 | 0 |  | 2 | 0
| Trial 450 | 3 | -3 |  | 3 | 3
| Trial 451 | 1 | -3 |  | 1 | 3
| Trial 452 | 1 | -2 |  | 1 | 2
| Trial 453 | 0 | -2 |  | 0 | 2
| Trial 454 | 3 | 0 |  | 3 | 0
| Trial 455 | 0 | -2 |  | 0 | 2
| Trial 456 | 5 | 0 |  | 5 | 0
| Trial 457 | 1 | -1 |  | 1 | 1
| Trial 458 | 1 | 0 |  | 1 | 0
| Trial 459 | 5 | -1 |  | 5 | 1
| Trial 460 | 3 | -1 |  | 3 | 1
| Trial 461 | 3 | -1 |  | 3 | 1
| Trial 462 | -2 | -2 |  | 2 | 2
| Trial 463 | 0 | 0 |  | 0 | 0
| Trial 464 | 1 | -3 |  | 1 | 3
| Trial 465 | 3 | -2 |  | 3 | 2
| Trial 466 | 4 | 0 |  | 4 | 0
| Trial 467 | 1 | -1 |  | 1 | 1
| Trial 468 | 4 | -1 |  | 4 | 1
| Trial 469 | -1 | -5 |  | 1 | 5
| Trial 470 | 6 | 0 |  | 6 | 0
| Trial 471 | 3 | -1 |  | 3 | 1
| Trial 472 | 2 | -1 |  | 2 | 1
| Trial 473 | 3 | -2 |  | 3 | 2
| Trial 474 | 3 | 0 |  | 3 | 0
| Trial 475 | 6 | -2 |  | 6 | 2
| Trial 476 | 3 | -2 |  | 3 | 2
| Trial 477 | 0 | -3 |  | 0 | 3
| Trial 478 | 0 | -1 |  | 0 | 1
| Trial 479 | 0 | -1 |  | 0 | 1
| Trial 480 | 2 | 0 |  | 2 | 0
| Trial 481 | -4 | -1 |  | 4 | 1
| Trial 482 | -1 | -2 |  | 1 | 2
| Trial 483 | 2 | -2 |  | 2 | 2
| Trial 484 | 2 | 0 |  | 2 | 0
| Trial 485 | 3 | -2 |  | 3 | 2
| Trial 486 | 2 | -1 |  | 2 | 1
| Trial 487 | 3 | -1 |  | 3 | 1
| Trial 488 | 5 | -1 |  | 5 | 1
| Trial 489 | 0 | -1 |  | 0 | 1
| Trial 490 | 5 | -1 |  | 5 | 1
| Trial 491 | 1 | 0 |  | 1 | 0
| Trial 492 | 3 | 0 |  | 3 | 0
| Trial 493 | 2 | 0 |  | 2 | 0
| Trial 494 | 3 | -1 |  | 3 | 1
| Trial 495 | 4 | -2 |  | 4 | 2
| Trial 496 | 2 | -3 |  | 2 | 3
| Trial 497 | 5 | 0 |  | 5 | 0
| Trial 498 | 1 | -2 |  | 1 | 2
| Trial 499 | 4 | -2 |  | 4 | 2
| Trial 500 | 1 | -3 |  | 1 | 3
| Trial 501 | 2 | -1 |  | 2 | 1
| Trial 502 | 1 | -2 |  | 1 | 2
| Trial 503 | 3 | -1 |  | 3 | 1
| Trial 504 | 1 | -1 |  | 1 | 1
| Trial 505 | 4 | -2 |  | 4 | 2
| Trial 506 | 3 | -2 |  | 3 | 2
| Trial 507 | -3 | -1 |  | 3 | 1
| Trial 508 | -1 | -2 |  | 1 | 2
| Trial 509 | 4 | 0 |  | 4 | 0
| Trial 510 | 2 | -1 |  | 2 | 1
| Trial 511 | -1 | -3 |  | 1 | 3
| Trial 512 | 0 | -1 |  | 0 | 1
| Trial 513 | 2 | -2 |  | 2 | 2
| Trial 514 | 3 | -3 |  | 3 | 3
| Trial 515 | 2 | 0 |  | 2 | 0
| Trial 516 | 1 | -3 |  | 1 | 3
| Trial 517 | 2 | 0 |  | 2 | 0
| Trial 518 | 3 | -1 |  | 3 | 1
| Trial 519 | -2 | -2 |  | 2 | 2
| Trial 520 | 2 | -1 |  | 2 | 1
| Trial 521 | 3 | -1 |  | 3 | 1
| Trial 522 | 0 | -1 |  | 0 | 1
| Trial 523 | 3 | 0 |  | 3 | 0
| Trial 524 | 3 | -1 |  | 3 | 1
| Trial 525 | 1 | 0 |  | 1 | 0
| Trial 526 | 1 | -1 |  | 1 | 1
| Trial 527 | 1 | -2 |  | 1 | 2
| Trial 528 | 5 | -1 |  | 5 | 1
| Trial 529 | 3 | -1 |  | 3 | 1
| Trial 530 | 0 | 0 |  | 0 | 0
| Trial 531 | 3 | -1 |  | 3 | 1
| Trial 532 | 3 | 0 |  | 3 | 0
| Trial 533 | 1 | 0 |  | 1 | 0
| Trial 534 | 3 | -1 |  | 3 | 1
| Trial 535 | 0 | 0 |  | 0 | 0
| Trial 536 | 4 | -1 |  | 4 | 1
| Trial 537 | 4 | 0 |  | 4 | 0
| Trial 538 | 0 | -2 |  | 0 | 2
| Trial 539 | 2 | 0 |  | 2 | 0
| Trial 540 | 1 | -4 |  | 1 | 4
| Trial 541 | 0 | 0 |  | 0 | 0
| Trial 542 | 2 | -1 |  | 2 | 1
| Trial 543 | 3 | 0 |  | 3 | 0
| Trial 544 | 3 | 0 |  | 3 | 0
| Trial 545 | 4 | -2 |  | 4 | 2
| Trial 546 | 1 | 0 |  | 1 | 0
| Trial 547 | 4 | 0 |  | 4 | 0
| Trial 548 | 2 | -2 |  | 2 | 2
| Trial 549 | 2 | 0 |  | 2 | 0
| Trial 550 | 2 | -1 |  | 2 | 1
| Trial 551 | 3 | -2 |  | 3 | 2
| Trial 552 | 1 | 0 |  | 1 | 0
| Trial 553 | 4 | -1 |  | 4 | 1
| Trial 554 | -1 | 0 |  | 1 | 0
| Trial 555 | 2 | -1 |  | 2 | 1
| Trial 556 | 3 | -1 |  | 3 | 1
| Trial 557 | 3 | -1 |  | 3 | 1
| Trial 558 | 5 | -1 |  | 5 | 1
| Trial 559 | 2 | 0 |  | 2 | 0
| Trial 560 | 2 | 0 |  | 2 | 0
| Trial 561 | 0 | 0 |  | 0 | 0
| Trial 562 | 3 | 0 |  | 3 | 0
| Trial 563 | 2 | -1 |  | 2 | 1
| Trial 564 | 0 | -2 |  | 0 | 2
| Trial 565 | 4 | 0 |  | 4 | 0
| Trial 566 | -1 | -1 |  | 1 | 1
| Trial 567 | 4 | 0 |  | 4 | 0
| Trial 568 | 4 | -2 |  | 4 | 2
| Trial 569 | 1 | 0 |  | 1 | 0
| Trial 570 | 2 | -1 |  | 2 | 1
| Trial 571 | 4 | 0 |  | 4 | 0
| Trial 572 | 1 | -2 |  | 1 | 2
| Trial 573 | 2 | -2 |  | 2 | 2
| Trial 574 | 4 | -1 |  | 4 | 1
| Trial 575 | 2 | -1 |  | 2 | 1
| Trial 576 | 0 | -1 |  | 0 | 1
| Trial 577 | 3 | 0 |  | 3 | 0
| Trial 578 | 0 | -1 |  | 0 | 1
| Trial 579 | 0 | 0 |  | 0 | 0
| Trial 580 | 2 | -2 |  | 2 | 2
| Trial 581 | 2 | -5 |  | 2 | 5
| Trial 582 | 4 | 0 |  | 4 | 0
| Trial 583 | 3 | 0 |  | 3 | 0
| Trial 584 | 1 | -1 |  | 1 | 1
| Trial 585 | -2 | 0 |  | 2 | 0
| Trial 586 | 4 | -1 |  | 4 | 1
| Trial 587 | 3 | -2 |  | 3 | 2
| Trial 588 | 6 | 0 |  | 6 | 0
| Trial 589 | 4 | 0 |  | 4 | 0
| Trial 590 | 1 | 0 |  | 1 | 0
| Trial 591 | 1 | -1 |  | 1 | 1
| Trial 592 | 4 | -3 |  | 4 | 3
| Trial 593 | 4 | -1 |  | 4 | 1
| Trial 594 | 2 | 0 |  | 2 | 0
| Trial 595 | 2 | -1 |  | 2 | 1
| Trial 596 | 4 | 0 |  | 4 | 0
| Trial 597 | 2 | -1 |  | 2 | 1
| Trial 598 | 1 | 0 |  | 1 | 0
| Trial 599 | 1 | -2 |  | 1 | 2
| Trial 600 | 1 | -2 |  | 1 | 2
| Trial 601 | 2 | -1 |  | 2 | 1
| Trial 602 | 2 | -2 |  | 2 | 2
| Trial 603 | 3 | -3 |  | 3 | 3
| Trial 604 | 2 | 0 |  | 2 | 0
| Trial 605 | 1 | -2 |  | 1 | 2
| Trial 606 | 2 | -1 |  | 2 | 1
| Trial 607 | 0 | -2 |  | 0 | 2
| Trial 608 | 4 | -1 |  | 4 | 1
| Trial 609 | 0 | -2 |  | 0 | 2
| Trial 610 | 2 | -2 |  | 2 | 2
| Trial 611 | 1 | -2 |  | 1 | 2
| Trial 612 | 2 | 0 |  | 2 | 0
| Trial 613 | 2 | 0 |  | 2 | 0
| Trial 614 | -1 | 0 |  | 1 | 0
| Trial 615 | 0 | -1 |  | 0 | 1
| Trial 616 | 2 | 0 |  | 2 | 0
| Trial 617 | 1 | -1 |  | 1 | 1
| Trial 618 | 5 | -1 |  | 5 | 1
| Trial 619 | 3 | -2 |  | 3 | 2
| Trial 620 | 5 | -1 |  | 5 | 1
| Trial 621 | 5 | -1 |  | 5 | 1
| Trial 622 | 4 | -3 |  | 4 | 3
| Trial 623 | 4 | -2 |  | 4 | 2
| Trial 624 | 5 | -2 |  | 5 | 2
| Trial 625 | 0 | 0 |  | 0 | 0
| Trial 626 | 4 | -1 |  | 4 | 1
| Trial 627 | 3 | 0 |  | 3 | 0
| Trial 628 | 2 | -2 |  | 2 | 2
| Trial 629 | 2 | -1 |  | 2 | 1
| Trial 630 | 0 | -1 |  | 0 | 1
| Trial 631 | 4 | -1 |  | 4 | 1
| Trial 632 | 2 | -1 |  | 2 | 1
| Trial 633 | 1 | 0 |  | 1 | 0
| Trial 634 | 4 | -1 |  | 4 | 1
| Trial 635 | 0 | -1 |  | 0 | 1
| Trial 636 | 3 | -1 |  | 3 | 1
| Trial 637 | 1 | -2 |  | 1 | 2
| Trial 638 | 3 | -1 |  | 3 | 1
| Trial 639 | 3 | -1 |  | 3 | 1
| Trial 640 | 3 | -1 |  | 3 | 1
| Trial 641 | 5 | 0 |  | 5 | 0
| Trial 642 | 2 | -2 |  | 2 | 2
| Trial 643 | 5 | 0 |  | 5 | 0
| Trial 644 | 2 | -2 |  | 2 | 2
| Trial 645 | 2 | 0 |  | 2 | 0
| Trial 646 | 4 | -1 |  | 4 | 1
| Trial 647 | -1 | -2 |  | 1 | 2
| Trial 648 | 2 | 0 |  | 2 | 0
| Trial 649 | 1 | -1 |  | 1 | 1
| Trial 650 | 1 | 0 |  | 1 | 0
| Trial 651 | 5 | -3 |  | 5 | 3
| Trial 652 | 1 | -1 |  | 1 | 1
| Trial 653 | 4 | -1 |  | 4 | 1
| Trial 654 | 5 | 0 |  | 5 | 0
| Trial 655 | -1 | -2 |  | 1 | 2
| Trial 656 | 4 | -1 |  | 4 | 1
| Trial 657 | 5 | -1 |  | 5 | 1
| Trial 658 | 5 | -2 |  | 5 | 2
| Trial 659 | 1 | -1 |  | 1 | 1
| Trial 660 | 4 | 0 |  | 4 | 0
| Trial 661 | 4 | -1 |  | 4 | 1
| Trial 662 | 5 | 0 |  | 5 | 0
| Trial 663 | 3 | 0 |  | 3 | 0
| Trial 664 | 1 | -1 |  | 1 | 1
| Trial 665 | 6 | 0 |  | 6 | 0
| Trial 666 | -2 | 0 |  | 2 | 0
| Trial 667 | 6 | -1 |  | 6 | 1
| Trial 668 | 5 | 0 |  | 5 | 0
| Trial 669 | 2 | -1 |  | 2 | 1
| Trial 670 | 0 | -1 |  | 0 | 1
| Trial 671 | 2 | -1 |  | 2 | 1
| Trial 672 | 2 | 0 |  | 2 | 0
| Trial 673 | 3 | 0 |  | 3 | 0
| Trial 674 | 3 | 0 |  | 3 | 0
| Trial 675 | -1 | 0 |  | 1 | 0
| Trial 676 | 1 | -3 |  | 1 | 3
| Trial 677 | 2 | 0 |  | 2 | 0
| Trial 678 | 0 | 0 |  | 0 | 0
| Trial 679 | 3 | -1 |  | 3 | 1
| Trial 680 | 1 | 0 |  | 1 | 0
| Trial 681 | 5 | 0 |  | 5 | 0
| Trial 682 | 5 | -2 |  | 5 | 2
| Trial 683 | 3 | 0 |  | 3 | 0
| Trial 684 | 2 | -1 |  | 2 | 1
| Trial 685 | 0 | -1 |  | 0 | 1
| Trial 686 | 6 | 0 |  | 6 | 0
| Trial 687 | 4 | -1 |  | 4 | 1
| Trial 688 | 2 | -1 |  | 2 | 1
| Trial 689 | 1 | 0 |  | 1 | 0
| Trial 690 | 2 | -1 |  | 2 | 1
| Trial 691 | 3 | -2 |  | 3 | 2
| Trial 692 | 6 | -1 |  | 6 | 1
| Trial 693 | 2 | -1 |  | 2 | 1
| Trial 694 | 2 | -1 |  | 2 | 1
| Trial 695 | 1 | -2 |  | 1 | 2
| Trial 696 | 0 | 0 |  | 0 | 0
| Trial 697 | 0 | -2 |  | 0 | 2
| Trial 698 | 2 | -1 |  | 2 | 1
| Trial 699 | 2 | 0 |  | 2 | 0
| Trial 700 | 0 | -1 |  | 0 | 1
| Trial 701 | 3 | -1 |  | 3 | 1
| Trial 702 | 1 | -1 |  | 1 | 1
| Trial 703 | -2 | -1 |  | 2 | 1
| Trial 704 | 2 | -2 |  | 2 | 2
| Trial 705 | 4 | -1 |  | 4 | 1
| Trial 706 | 4 | -1 |  | 4 | 1
| Trial 707 | 5 | -1 |  | 5 | 1
| Trial 708 | -2 | -1 |  | 2 | 1
| Trial 709 | -1 | 0 |  | 1 | 0
| Trial 710 | 0 | 0 |  | 0 | 0
| Trial 711 | 2 | -1 |  | 2 | 1
| Trial 712 | 6 | -1 |  | 6 | 1
| Trial 713 | 2 | -1 |  | 2 | 1
| Trial 714 | -1 | -1 |  | 1 | 1
| Trial 715 | 4 | -2 |  | 4 | 2
| Trial 716 | 1 | -3 |  | 1 | 3
| Trial 717 | -2 | 0 |  | 2 | 0
| Trial 718 | 1 | 0 |  | 1 | 0
| Trial 719 | 3 | -2 |  | 3 | 2
| Trial 720 | 2 | 0 |  | 2 | 0
| Trial 721 | -1 | -1 |  | 1 | 1
| Trial 722 | 2 | -3 |  | 2 | 3
| Trial 723 | -3 | -1 |  | 3 | 1
| Trial 724 | 2 | -1 |  | 2 | 1
| Trial 725 | 2 | -4 |  | 2 | 4
| Trial 726 | 1 | 0 |  | 1 | 0
| Trial 727 | 1 | -3 |  | 1 | 3
| Trial 728 | 3 | -2 |  | 3 | 2
| Trial 729 | 3 | -1 |  | 3 | 1
| Trial 730 | 3 | -2 |  | 3 | 2
| Trial 731 | 4 | -3 |  | 4 | 3
| Trial 732 | 0 | 0 |  | 0 | 0
| Trial 733 | 1 | 0 |  | 1 | 0
| Trial 734 | -1 | -5 |  | 1 | 5
| Trial 735 | 2 | -2 |  | 2 | 2
| Trial 736 | 5 | 0 |  | 5 | 0
| Trial 737 | 2 | -1 |  | 2 | 1
| Trial 738 | 3 | -1 |  | 3 | 1
| Trial 739 | 3 | -1 |  | 3 | 1
| Trial 740 | 2 | -1 |  | 2 | 1
| Trial 741 | 0 | 0 |  | 0 | 0
| Trial 742 | 4 | -2 |  | 4 | 2
| Trial 743 | 1 | 0 |  | 1 | 0
| Trial 744 | 3 | -2 |  | 3 | 2
| Trial 745 | 0 | -3 |  | 0 | 3
| Trial 746 | 0 | -4 |  | 0 | 4
| Trial 747 | 1 | -2 |  | 1 | 2
| Trial 748 | 4 | -1 |  | 4 | 1
| Trial 749 | 1 | -2 |  | 1 | 2
| Trial 750 | 4 | -2 |  | 4 | 2
| Trial 751 | 2 | -1 |  | 2 | 1
| Trial 752 | 1 | -3 |  | 1 | 3
| Trial 753 | -1 | -1 |  | 1 | 1
| Trial 754 | 3 | 0 |  | 3 | 0
| Trial 755 | 0 | -2 |  | 0 | 2
| Trial 756 | 3 | -1 |  | 3 | 1
| Trial 757 | 2 | -4 |  | 2 | 4
| Trial 758 | 1 | -1 |  | 1 | 1
| Trial 759 | 3 | -1 |  | 3 | 1
| Trial 760 | 4 | -1 |  | 4 | 1
| Trial 761 | -1 | -2 |  | 1 | 2
| Trial 762 | 3 | 0 |  | 3 | 0
| Trial 763 | 3 | -3 |  | 3 | 3
| Trial 764 | 0 | -1 |  | 0 | 1
| Trial 765 | 2 | 0 |  | 2 | 0
| Trial 766 | 1 | -1 |  | 1 | 1
| Trial 767 | 2 | 0 |  | 2 | 0
| Trial 768 | 4 | 0 |  | 4 | 0
| Trial 769 | 0 | -1 |  | 0 | 1
| Trial 770 | 3 | 0 |  | 3 | 0
| Trial 771 | 3 | -2 |  | 3 | 2
| Trial 772 | 1 | -1 |  | 1 | 1
| Trial 773 | 6 | 0 |  | 6 | 0
| Trial 774 | 3 | -2 |  | 3 | 2
| Trial 775 | 2 | -2 |  | 2 | 2
| Trial 776 | 4 | -2 |  | 4 | 2
| Trial 777 | -1 | -1 |  | 1 | 1
| Trial 778 | 2 | -1 |  | 2 | 1
| Trial 779 | 3 | -3 |  | 3 | 3
| Trial 780 | 7 | 0 |  | 7 | 0
| Trial 781 | 1 | -2 |  | 1 | 2
| Trial 782 | 2 | -3 |  | 2 | 3
| Trial 783 | 0 | -3 |  | 0 | 3
| Trial 784 | -1 | -1 |  | 1 | 1
| Trial 785 | 2 | -1 |  | 2 | 1
| Trial 786 | 5 | -1 |  | 5 | 1
| Trial 787 | 3 | -3 |  | 3 | 3
| Trial 788 | -3 | -4 |  | 3 | 4
| Trial 789 | -1 | -1 |  | 1 | 1
| Trial 790 | 4 | -1 |  | 4 | 1
| Trial 791 | 2 | -2 |  | 2 | 2
| Trial 792 | 0 | -1 |  | 0 | 1
| Trial 793 | 4 | -3 |  | 4 | 3
| Trial 794 | 4 | -1 |  | 4 | 1
| Trial 795 | 2 | -1 |  | 2 | 1
| Trial 796 | 3 | -3 |  | 3 | 3
| Trial 797 | 3 | -1 |  | 3 | 1
| Trial 798 | 3 | -4 |  | 3 | 4
| Trial 799 | 2 | -4 |  | 2 | 4
| Trial 800 | 2 | -2 |  | 2 | 2
| Trial 801 | 0 | -1 |  | 0 | 1
| Trial 802 | 1 | -1 |  | 1 | 1
| Trial 803 | 3 | -2 |  | 3 | 2
| Trial 804 | 0 | -1 |  | 0 | 1
| Trial 805 | 3 | 0 |  | 3 | 0
| Trial 806 | 5 | 0 |  | 5 | 0
| Trial 807 | 2 | 0 |  | 2 | 0
| Trial 808 | 6 | 0 |  | 6 | 0
| Trial 809 | 5 | 0 |  | 5 | 0
| Trial 810 | 3 | -2 |  | 3 | 2
| Trial 811 | 2 | -2 |  | 2 | 2
| Trial 812 | 3 | -2 |  | 3 | 2
| Trial 813 | 3 | -2 |  | 3 | 2
| Trial 814 | 5 | -1 |  | 5 | 1
| Trial 815 | 2 | -2 |  | 2 | 2
| Trial 816 | 4 | -1 |  | 4 | 1
| Trial 817 | 3 | 0 |  | 3 | 0
| Trial 818 | 1 | -1 |  | 1 | 1
| Trial 819 | 2 | -1 |  | 2 | 1
| Trial 820 | 4 | 0 |  | 4 | 0
| Trial 821 | 1 | -2 |  | 1 | 2
| Trial 822 | 2 | -3 |  | 2 | 3
| Trial 823 | -2 | -1 |  | 2 | 1
| Trial 824 | -1 | -1 |  | 1 | 1
| Trial 825 | -1 | -2 |  | 1 | 2
| Trial 826 | 4 | -2 |  | 4 | 2
| Trial 827 | 3 | 0 |  | 3 | 0
| Trial 828 | 1 | 0 |  | 1 | 0
| Trial 829 | 3 | -2 |  | 3 | 2
| Trial 830 | -2 | -2 |  | 2 | 2
| Trial 831 | 1 | -1 |  | 1 | 1
| Trial 832 | 0 | -2 |  | 0 | 2
| Trial 833 | 2 | -2 |  | 2 | 2
| Trial 834 | 3 | -1 |  | 3 | 1
| Trial 835 | 2 | -2 |  | 2 | 2
| Trial 836 | 6 | -1 |  | 6 | 1
| Trial 837 | 2 | 0 |  | 2 | 0
| Trial 838 | 4 | -3 |  | 4 | 3
| Trial 839 | 3 | -3 |  | 3 | 3
| Trial 840 | 4 | 0 |  | 4 | 0
| Trial 841 | 3 | -3 |  | 3 | 3
| Trial 842 | 2 | -1 |  | 2 | 1
| Trial 843 | 1 | -3 |  | 1 | 3
| Trial 844 | 2 | 0 |  | 2 | 0
| Trial 845 | 4 | -1 |  | 4 | 1
| Trial 846 | -1 | -2 |  | 1 | 2
| Trial 847 | 1 | 0 |  | 1 | 0
| Trial 848 | 2 | -3 |  | 2 | 3
| Trial 849 | 1 | 0 |  | 1 | 0
| Trial 850 | 1 | 0 |  | 1 | 0
| Trial 851 | 2 | -1 |  | 2 | 1
| Trial 852 | -1 | -2 |  | 1 | 2
| Trial 853 | 5 | 0 |  | 5 | 0
| Trial 854 | 4 | 0 |  | 4 | 0
| Trial 855 | 2 | -2 |  | 2 | 2
| Trial 856 | 3 | -2 |  | 3 | 2
| Trial 857 | 2 | -1 |  | 2 | 1
| Trial 858 | 1 | 0 |  | 1 | 0
| Trial 859 | 1 | -2 |  | 1 | 2
| Trial 860 | 3 | -1 |  | 3 | 1
| Trial 861 | 3 | 0 |  | 3 | 0
| Trial 862 | 0 | -2 |  | 0 | 2
| Trial 863 | 5 | 0 |  | 5 | 0
| Trial 864 | 3 | -1 |  | 3 | 1
| Trial 865 | -1 | 0 |  | 1 | 0
| Trial 866 | 2 | -3 |  | 2 | 3
| Trial 867 | 4 | -2 |  | 4 | 2
| Trial 868 | 1 | -3 |  | 1 | 3
| Trial 869 | 4 | -1 |  | 4 | 1
| Trial 870 | 3 | -1 |  | 3 | 1
| Trial 871 | 4 | 0 |  | 4 | 0
| Trial 872 | 2 | -5 |  | 2 | 5
| Trial 873 | -2 | -1 |  | 2 | 1
| Trial 874 | 4 | -2 |  | 4 | 2
| Trial 875 | 4 | 0 |  | 4 | 0
| Trial 876 | 1 | 0 |  | 1 | 0
| Trial 877 | 1 | -2 |  | 1 | 2
| Trial 878 | 4 | 0 |  | 4 | 0
| Trial 879 | 1 | -2 |  | 1 | 2
| Trial 880 | 4 | -2 |  | 4 | 2
| Trial 881 | 4 | 0 |  | 4 | 0
| Trial 882 | 2 | -1 |  | 2 | 1
| Trial 883 | 5 | -1 |  | 5 | 1
| Trial 884 | 0 | -1 |  | 0 | 1
| Trial 885 | 3 | -1 |  | 3 | 1
| Trial 886 | -1 | -1 |  | 1 | 1
| Trial 887 | 5 | -1 |  | 5 | 1
| Trial 888 | -1 | -1 |  | 1 | 1
| Trial 889 | 6 | 0 |  | 6 | 0
| Trial 890 | 1 | -2 |  | 1 | 2
| Trial 891 | 1 | 0 |  | 1 | 0
| Trial 892 | 4 | -1 |  | 4 | 1
| Trial 893 | 1 | -1 |  | 1 | 1
| Trial 894 | 4 | -2 |  | 4 | 2
| Trial 895 | 5 | -1 |  | 5 | 1
| Trial 896 | 4 | -1 |  | 4 | 1
| Trial 897 | 3 | 0 |  | 3 | 0
| Trial 898 | 5 | -1 |  | 5 | 1
| Trial 899 | 2 | 0 |  | 2 | 0
| Trial 900 | 2 | -3 |  | 2 | 3
| Trial 901 | 4 | -2 |  | 4 | 2
| Trial 902 | 3 | -1 |  | 3 | 1
| Trial 903 | 4 | 0 |  | 4 | 0
| Trial 904 | 2 | -2 |  | 2 | 2
| Trial 905 | 2 | -2 |  | 2 | 2
| Trial 906 | 1 | -2 |  | 1 | 2
| Trial 907 | 3 | -2 |  | 3 | 2
| Trial 908 | 1 | -2 |  | 1 | 2
| Trial 909 | 5 | -1 |  | 5 | 1
| Trial 910 | 0 | -1 |  | 0 | 1
| Trial 911 | 4 | -2 |  | 4 | 2
| Trial 912 | 4 | -1 |  | 4 | 1
| Trial 913 | 2 | -1 |  | 2 | 1
| Trial 914 | -1 | 0 |  | 1 | 0
| Trial 915 | 1 | -1 |  | 1 | 1
| Trial 916 | 4 | -1 |  | 4 | 1
| Trial 917 | 2 | -1 |  | 2 | 1
| Trial 918 | 1 | -2 |  | 1 | 2
| Trial 919 | 5 | 0 |  | 5 | 0
| Trial 920 | 2 | -2 |  | 2 | 2
| Trial 921 | 4 | -1 |  | 4 | 1
| Trial 922 | 3 | -1 |  | 3 | 1
| Trial 923 | 2 | 0 |  | 2 | 0
| Trial 924 | 2 | 0 |  | 2 | 0
| Trial 925 | 0 | -2 |  | 0 | 2
| Trial 926 | 0 | -2 |  | 0 | 2
| Trial 927 | 1 | -3 |  | 1 | 3
| Trial 928 | 2 | -2 |  | 2 | 2
| Trial 929 | 2 | -2 |  | 2 | 2
| Trial 930 | 2 | -1 |  | 2 | 1
| Trial 931 | 4 | -3 |  | 4 | 3
| Trial 932 | 4 | -1 |  | 4 | 1
| Trial 933 | 5 | -1 |  | 5 | 1
| Trial 934 | 0 | 0 |  | 0 | 0
| Trial 935 | -2 | -1 |  | 2 | 1
| Trial 936 | 3 | -1 |  | 3 | 1
| Trial 937 | 0 | -2 |  | 0 | 2
| Trial 938 | 4 | -1 |  | 4 | 1
| Trial 939 | 0 | -2 |  | 0 | 2
| Trial 940 | 1 | 0 |  | 1 | 0
| Trial 941 | 2 | -2 |  | 2 | 2
| Trial 942 | 2 | 0 |  | 2 | 0
| Trial 943 | 3 | -1 |  | 3 | 1
| Trial 944 | 2 | -1 |  | 2 | 1
| Trial 945 | 2 | 0 |  | 2 | 0
| Trial 946 | 2 | -2 |  | 2 | 2
| Trial 947 | 2 | 0 |  | 2 | 0
| Trial 948 | 1 | -3 |  | 1 | 3
| Trial 949 | 5 | -2 |  | 5 | 2
| Trial 950 | 2 | -2 |  | 2 | 2
| Trial 951 | 5 | -3 |  | 5 | 3
| Trial 952 | 0 | -5 |  | 0 | 5
| Trial 953 | 4 | 0 |  | 4 | 0
| Trial 954 | 4 | -1 |  | 4 | 1
| Trial 955 | 5 | -2 |  | 5 | 2
| Trial 956 | 3 | -1 |  | 3 | 1
| Trial 957 | 5 | -1 |  | 5 | 1
| Trial 958 | 0 | -2 |  | 0 | 2
| Trial 959 | 3 | -3 |  | 3 | 3
| Trial 960 | 3 | -1 |  | 3 | 1
| Trial 961 | 3 | -2 |  | 3 | 2
| Trial 962 | 0 | -2 |  | 0 | 2
| Trial 963 | 4 | -2 |  | 4 | 2
| Trial 964 | 3 | -1 |  | 3 | 1
| Trial 965 | 2 | -1 |  | 2 | 1
| Trial 966 | 3 | -1 |  | 3 | 1
| Trial 967 | -1 | 0 |  | 1 | 0
| Trial 968 | 3 | 0 |  | 3 | 0
| Trial 969 | 1 | -1 |  | 1 | 1
| Trial 970 | 0 | 0 |  | 0 | 0
| Trial 971 | -1 | -2 |  | 1 | 2
| Trial 972 | 1 | -2 |  | 1 | 2
| Trial 973 | -2 | 0 |  | 2 | 0
| Trial 974 | 4 | -1 |  | 4 | 1
| Trial 975 | 2 | -2 |  | 2 | 2
| Trial 976 | 2 | -1 |  | 2 | 1
| Trial 977 | 3 | 0 |  | 3 | 0
| Trial 978 | 1 | -2 |  | 1 | 2
| Trial 979 | 3 | -1 |  | 3 | 1
| Trial 980 | 0 | 0 |  | 0 | 0
| Trial 981 | 4 | -2 |  | 4 | 2
| Trial 982 | 3 | -2 |  | 3 | 2
| Trial 983 | 1 | -1 |  | 1 | 1
| Trial 984 | 2 | 0 |  | 2 | 0
| Trial 985 | 3 | -1 |  | 3 | 1
| Trial 986 | 2 | 0 |  | 2 | 0
| Trial 987 | 4 | -1 |  | 4 | 1
| Trial 988 | 1 | 0 |  | 1 | 0
| Trial 989 | 5 | 0 |  | 5 | 0
| Trial 990 | 1 | -2 |  | 1 | 2
| Trial 991 | 0 | -1 |  | 0 | 1
| Trial 992 | 3 | -1 |  | 3 | 1
| Trial 993 | 3 | 0 |  | 3 | 0
| Trial 994 | 3 | -2 |  | 3 | 2
| Trial 995 | 3 | -2 |  | 3 | 2
| Trial 996 | 3 | -1 |  | 3 | 1
| Trial 997 | 4 | 0 |  | 4 | 0
| Trial 998 | 0 | -2 |  | 0 | 2
| Trial 999 | 2 | -1 |  | 2 | 1
| Trial 1000 | 3 | -1 |  | 3 | 1

## Problem 1
Adrian Harris
Professor Blau
OPR 3450
2019-05-26
Problem One
| Venture | A | A | A | B | B | B | C
| Return (in $ millions) | -0.5 | 0.1 | 1 | -1 | 1 | 3 | 0.125
| Probability | 25% | 50% | 25% | 35% | 60% | 5% | 100%
| Certainty Equvalence |  | x |  |  | y |  | z
| X | 0.175 |  |  | a. The numberical value of z is 125,000
| Y | 0.4 |  |  | b. To maximize expected value VL should invest in B
| Z | 0.125 |  |  | c. If VL invest in C the values of x and y must have been lower that 125,000
d. If VL invest in A the values of X was higher than 125,000 and the value of Y was lower.

## Problem 7 Last value method
Adrian Harris
Professor Blau |  |  |  | Avg Number | Seasonal Factor | Seasonally Adjusted Call Volume | Seasonally Adjusted Forecast | Actual | Forecasting Error
OPR 3450 |  | 1 | Jan | 68 | 0.9 | 75.5556
2019-05-26 |  | 1 | Feb | 71 | 0.88 | 80.6818 | 75.5556 | 66.4889 | 4.5111
Final |  | 1 | Mar | 66 | 0.91 | 72.5275 | 80.6818 | 73.4205 | 7.4205
Last value |  | 1 | Apr | 72 | 0.93 | 77.4194 | 72.5275 | 67.4505 | 4.5495
MAD | 2.4585 | 1 | May | 77 | 0.96 | 80.2083 | 77.4194 | 74.3226 | 2.6774
MSE | 8.3411 | 1 | Jun | 85 | 1.09 | 77.9817 | 80.2083 | 87.4271 | 2.4271
Seasonality | Monthly | 1 | Jul | 94 | 1.17 | 80.3419 | 77.9817 | 91.2385 | 2.7615
|  | 1 | Aug | 96 | 1.15 | 83.4783 | 80.3419 | 92.3932 | 3.6068
|  | 1 | Sep | 80 | 0.97 | 82.4742 | 83.4783 | 80.9739 | 0.97391
|  | 1 | Oct | 73 | 0.91 | 80.2198 | 82.4742 | 75.0515 | 2.0515
|  | 1 | Nov | 84 | 1.05 | 80 | 80.2198 | 84.2308 | 0.23077
|  | 1 | Dec | 89 | 1.08 | 82.4074 | 80 | 86.4 | 2.6
|  | 2 | Jan | 75 | 0.9 | 83.3333 | 82.4074 | 74.1667 | 0.83333
|  | 2 | Feb | 76 | 0.88 | 86.3636 | 83.3333 | 73.3333 | 2.6667
|  | 2 | Mar | 81 | 0.91 | 89.011 | 86.3636 | 78.5909 | 2.4091
|  | 2 | Apr | 84 | 0.93 | 90.3226 | 89.011 | 82.7802 | 1.2198
|  | 2 | May | 85 | 0.96 | 88.5417 | 90.3226 | 86.7097 | 1.7097
|  | 2 | Jun | 99 | 1.09 | 90.8257 | 88.5417 | 96.5104 | 2.4896
|  | 2 | Jul | 107 | 1.17 | 91.453 | 90.8257 | 106.2661 | 0.73394
|  | 2 | Aug | 108 | 1.15 | 93.913 | 91.453 | 105.1709 | 2.8291
|  | 2 | Sep | 94 | 0.97 | 96.9072 | 93.913 | 91.0957 | 2.9043
|  | 2 | Oct | 90 | 0.91 | 98.9011 | 96.9072 | 88.1856 | 1.8144
|  | 2 | Nov | 106 | 1.05 | 100.9524 | 98.9011 | 103.8462 | 2.1538
|  | 2 | Dec | 110 | 1.08 | 101.8519 | 100.9524 | 109.0286 | 0.97143
|  | 3 | Jan |  | 0.9 |  | 101.8519 | 91.6667

## Problem 7 Moving average
Adrian Harris
Professor Blau
OPR 3450 |  |  |  | Avg Number | Seasonal Factor | Seasonally Adjusted Call Volume | Seasonally Adjusted Forecast | Actual | Forecasting Error
2019-05-26 |  | 1 | Jan | 68 | 0.9 | 75.5556
Final |  | 1 | Feb | 71 | 0.88 | 80.6818
Moving Avg |  | 1 | Mar | 66 | 0.91 | 72.5275
MAD | 2.7928 | 1 | Apr | 72 | 0.93 | 77.4194 | 76.2549 | 70.9171 | 1.0829
MSE | 9.6825 | 1 | May | 77 | 0.96 | 80.2083 | 76.8762 | 73.8012 | 3.1988
|  | 1 | Jun | 85 | 1.09 | 77.9817 | 76.7184 | 83.623 | 1.377
|  | 1 | Jul | 94 | 1.17 | 80.3419 | 78.5364 | 91.8876 | 2.1124
|  | 1 | Aug | 96 | 1.15 | 83.4783 | 79.5106 | 91.4372 | 4.5628
|  | 1 | Sep | 80 | 0.97 | 82.4742 | 80.6006 | 78.1826 | 1.8174
|  | 1 | Oct | 73 | 0.91 | 80.2198 | 82.0981 | 74.7093 | 1.7093
|  | 1 | Nov | 84 | 1.05 | 80 | 82.0574 | 86.1603 | 2.1603
|  | 1 | Dec | 89 | 1.08 | 82.4074 | 80.898 | 87.3698 | 1.6302
|  | 2 | Jan | 75 | 0.9 | 83.3333 | 80.8757 | 72.7882 | 2.2118
|  | 2 | Feb | 76 | 0.88 | 86.3636 | 81.9136 | 72.084 | 3.916
|  | 2 | Mar | 81 | 0.91 | 89.011 | 84.0348 | 76.4717 | 4.5283
|  | 2 | Apr | 84 | 0.93 | 90.3226 | 86.236 | 80.1995 | 3.8005
|  | 2 | May | 85 | 0.96 | 88.5417 | 88.5657 | 85.0231 | 0.023106
|  | 2 | Jun | 99 | 1.09 | 90.8257 | 89.2917 | 97.328 | 1.672
|  | 2 | Jul | 107 | 1.17 | 91.453 | 89.8966 | 105.1791 | 1.8209
|  | 2 | Aug | 108 | 1.15 | 93.913 | 90.2734 | 103.8145 | 4.1855
|  | 2 | Sep | 94 | 0.97 | 96.9072 | 92.0639 | 89.302 | 4.698
|  | 2 | Oct | 90 | 0.91 | 98.9011 | 94.0911 | 85.6229 | 4.3771
|  | 2 | Nov | 106 | 1.05 | 100.9524 | 96.5738 | 101.4025 | 4.5975
|  | 2 | Dec | 110 | 1.08 | 101.8519 | 98.9202 | 106.8339 | 3.1661
|  | 3 | jan | 68 | 0.9 | 75.5556 | 100.5684 | 90.5116 | 22.5116

## Problem 7 exponential smoothing
Adrian Harris
Professor Blau
OPR 3450 |  | Year |  | Avg Number | Seasonal Factor | Seasonally Adjusted Call Volume | Seasonally Adjusted Forecast | Actual | Forecasting Error
2019-05-26 |  | 1 | Jan | 68 | 0.9 | 75.5556 | 78 | 70.2 | 2.2
Final |  | 1 | Feb | 71 | 0.88 | 80.6818 | 77.3889 | 68.1022 | 2.8978
Exp smoothing |  | 1 | Mar | 66 | 0.91 | 72.5275 | 78.2121 | 71.173 | 5.173
alpha | 0.25 | 1 | Apr | 72 | 0.93 | 77.4194 | 76.791 | 71.4156 | 0.58441
mad | 4.4929 | 1 | May | 77 | 0.96 | 80.2083 | 76.9481 | 73.8701 | 3.1299
mse | 34.2474 | 1 | Jun | 85 | 1.09 | 77.9817 | 77.7631 | 84.7618 | 0.23819
|  | 1 | Jul | 94 | 1.17 | 80.3419 | 77.8178 | 91.0468 | 2.9532
|  | 1 | Aug | 96 | 1.15 | 83.4783 | 78.4488 | 90.2161 | 5.7839
|  | 1 | Sep | 80 | 0.97 | 82.4742 | 79.7062 | 77.315 | 2.685
|  | 1 | Oct | 73 | 0.91 | 80.2198 | 80.3982 | 73.1623 | 0.16234
|  | 1 | Nov | 84 | 1.05 | 80 | 80.3536 | 84.3713 | 0.37125
|  | 1 | Dec | 89 | 1.08 | 82.4074 | 80.2652 | 86.6864 | 2.3136
|  | 2 | Jan | 75 | 0.9 | 83.3333 | 80.8007 | 72.7207 | 2.2793
|  | 2 | Feb | 76 | 0.88 | 86.3636 | 81.4339 | 71.6618 | 4.3382
|  | 2 | Mar | 81 | 0.91 | 89.011 | 82.6663 | 75.2264 | 5.7736
|  | 2 | Apr | 84 | 0.93 | 90.3226 | 84.2525 | 78.3548 | 5.6452
|  | 2 | May | 85 | 0.96 | 88.5417 | 85.77 | 82.3392 | 2.6608
|  | 2 | Jun | 99 | 1.09 | 90.8257 | 86.4629 | 94.2446 | 4.7554
|  | 2 | Jul | 107 | 1.17 | 91.453 | 87.5536 | 102.4377 | 4.5623
|  | 2 | Aug | 108 | 1.15 | 93.913 | 88.5285 | 101.8077 | 6.1923
|  | 2 | Sep | 94 | 0.97 | 96.9072 | 89.8746 | 87.1784 | 6.8216
|  | 2 | Oct | 90 | 0.91 | 98.9011 | 91.6328 | 83.3858 | 6.6142
|  | 2 | Nov | 106 | 1.05 | 100.9524 | 93.4498 | 98.1223 | 7.8777
|  | 2 | Dec | 110 | 1.08 | 101.8519 | 95.3255 | 102.9515 | 7.0485
|  | 3 | jan | 68 | 0.9 | 75.5556 | 96.9571 | 87.2614 | 19.2614

## Problem 7 exp smoothing with t
Adrian Harris
Professor Blau |  |  |  | Avg Number | Seasonal Factor | Seasonally adjust value | last trend | estimate trend | Seasonally adjusted value | actual forecast | Forecasting Error
OPR 3450 |  | 1 | Jan | 68 | 0.9 | 75.5556 |  | 0 | 78 | 70.2 | 2.2
2019-05-26 |  | 1 | Feb | 71 | 0.88 | 80.6818 | -0.61111 | -0.12222 | 77.2667 | 67.9947 | 3.0053
Final |  | 1 | Mar | 66 | 0.91 | 72.5275 | -2.5886 | -0.6155 | 77.505 | 70.5295 | 4.5295
Exp smoothing T |  | 1 | Apr | 72 | 0.93 | 77.4194 | 1.4017 | -0.21206 | 76.0485 | 70.7251 | 1.2749
alpha | 0.25 | 1 | May | 77 | 0.96 | 80.2083 | -0.39508 | -0.24866 | 76.1426 | 73.0969 | 3.9031
beta | 0.2 | 1 | Jun | 85 | 1.09 | 77.9817 | -0.48614 | -0.29616 | 76.8629 | 83.7805 | 1.2195
MAD | 2.294 | 1 | Jul | 94 | 1.17 | 80.3419 | 1.1303 | -0.010872 | 77.1317 | 90.2441 | 3.7559
MSE | 7.4028 | 1 | Aug | 96 | 1.15 | 83.4783 | 0.98572 | 0.18845 | 78.1227 | 89.8411 | 6.1589
trend | 0 | 1 | Sep | 80 | 0.97 | 82.4742 | 0.49224 | 0.2492 | 79.7108 | 77.3195 | 2.6805
int estimate | 78 | 1 | Oct | 73 | 0.91 | 80.2198 | 0.62746 | 0.32486 | 80.7265 | 73.4611 | 0.46111
|  | 1 | Nov | 84 | 1.05 | 80 | 0.70684 | 0.40125 | 81.0011 | 85.0511 | 1.0511
|  | 1 | Dec | 89 | 1.08 | 82.4074 | 0.80778 | 0.48256 | 81.2334 | 87.732 | 1.268
|  | 2 | Jan | 75 | 0.9 | 83.3333 | 0.4057 | 0.46719 | 81.9941 | 73.7947 | 1.2053
|  | 2 | Feb | 76 | 0.88 | 86.3636 | 1.3281 | 0.63937 | 82.9682 | 73.0121 | 2.9879
|  | 2 | Mar | 81 | 0.91 | 89.011 | 1.3925 | 0.78999 | 84.6071 | 76.9924 | 4.0076
|  | 2 | Apr | 84 | 0.93 | 90.3226 | 1.557 | 0.9434 | 86.6515 | 80.5859 | 3.4141
|  | 2 | May | 85 | 0.96 | 88.5417 | 1.0881 | 0.97233 | 88.5416 | 84.9999 | 9.1984e-05
|  | 2 | Jun | 99 | 1.09 | 90.8257 | 1.9886 | 1.1756 | 89.7172 | 97.7917 | 1.2083
|  | 2 | Jul | 107 | 1.17 | 91.453 | 1.0385 | 1.1482 | 91.1425 | 106.6367 | 0.3633
|  | 2 | Aug | 108 | 1.15 | 93.913 | 1.684 | 1.2553 | 92.4754 | 106.3468 | 1.6532
|  | 2 | Sep | 94 | 0.97 | 96.9072 | 1.7483 | 1.3539 | 94.1888 | 91.3631 | 2.6369
|  | 2 | Oct | 90 | 0.91 | 98.9011 | 1.7835 | 1.4398 | 96.3082 | 87.6405 | 2.3595
|  | 2 | Nov | 106 | 1.05 | 100.9524 | 2.1024 | 1.5723 | 98.5288 | 103.4552 | 2.5448
|  | 2 | Dec | 110 | 1.08 | 101.8519 | 1.8903 | 1.6359 | 100.7706 | 108.8323 | 1.1677
|  | 3 | jan | 68 | 0.9 | 75.5556 | -4.8927 | 0.33021 | 101.3711 | 91.234 | 23.234

## Problem 8
Adrian Harris
Professor Blau
OPR 3450 |  |  |  | JV | [6 empty] | Pr
2019-05-26 |  |  | San fran Hit | San fran Miss | Totals |  | NH/SH | 36% |  |  | San fran Hit | San fran Miss | Totals | NH/SH | 66.67%
Final |  | National Hit | 18% | 2% | 20% |  | NM/SH | 64% |  | National Hit | 30% | 10% | 40% | NM/SH | 33.33%
Problem 8 |  | National Miss | 32% | 48% | 80% |  | NH/SM | 4% |  | National Miss | 15% | 45% | 60% | NH/SM | 18.18%
| Jv |  | 50% | 50% |  |  | NM/SM | 96% |  |  | 45% | 55% |  | NM/SM | 81.82%
90% | Hit nation Hit in San fran
40% | miss nation hit in san fran | Jv | Top level of Tree (No Pretest) |  |  | Jv | Lower level of tree (Pretest) |  | Pr
|  | Hit | 4400000 | 20% |  | Hit | 4400000 | 36% | Hit | 2300000 | 66.67%
| Pr | miss | 400000 | 80% |  | miss | 400000 | 64% | miss | 150000 | 33.33%
75% | Hit nation Hit in San fran | 1 | 500000 |  |  | 4 | 1240000 |  | 11 | 1283333.3333
25% | miss nation hit in san fran | Pr |  |  |  | Jv
|  | Hit | 2300000 | 40% |  | Hit | 4400000 | 4% | Hit | 2300000 | 18.18%
|  | miss | 150000 | 60% |  | miss | 400000 | 96% | miss | 150000 | 81.82%
|  | 2 | 660000 |  |  | 5 | -40000 |  | 12 | 240909.0909
|  | No invest |  |  |  | No invest |  |  | No invest
|  | 3 | -700000 |  |  | 6 | -600000 |  | 13 | -300000
[6 empty] | No invest |  |  | No invest
[6 empty] | 7 | -600000 |  | 14 | -300000
[6 empty] | 8 | 1240000 | 50% | 15 | 1283333.3333 | 45%
[6 empty] | 9 | -40000 | 50% | 16 | 240909.0909 | 55%
[6 empty] | 10 | 400000 |  | 17 | 610000

## Problem 6
Adrian Harris
Professor Blau
OPR 3450 |  | Area | Area | Area | Area
2019-05-26 | Com | 1 | 2 | 3 | 4
Final | 0 | 0 | 0 | 0 | 0
Problem 6 A | 1 | 4 | 6 | 5 | 3
| 2 | 7 | 8 | 9 | 7
| 3 | 9 | 10 | 11 | 12
| 4 | 12 | 11 | 10 | 14
| 5 | 15 | 12 | 9 | 16
| 6 | 16 | 13 | 8 | 17
| 7 | 17 | 14 | 7 | 18
| s | Fo(S) | F1(S) | F2(S) | F3(S) | F4(s)
| 0 | 0 | 0 | 0 | 0 | 0
| 1 | 0 | 4 | 6 | 6 | 6
| 2 | 0 | 7 | 10 | 11 | 11
| 3 | 0 | 9 | 13 | 15 | 15
| 4 | 0 | 12 | 15 | 19 | 19
| 5 | 0 | 15 | 18 | 22 | 23
| 6 | 0 | 16 | 21 | 24 | 27
| 7 | 0 | 17 | 23 | 27 | 31

## Problem 6 5 coms
Adrian Harris
Professor Blau
OPR 3450
2019-05-26 |  | Area | Area | Area | Area
Final | Com | 1 | 2 | 3 | 4
Problem 6 B | 0 | 0 | 0 | 0 | 0
| 1 | 4 | 6 | 5 | 3
| 2 | 7 | 8 | 9 | 7
| 3 | 9 | 10 | 11 | 12
| 4 | 12 | 11 | 10 | 14
| 5 | 15 | 12 | 9 | 16
| s | Fo(S) | F1(S) | F2(S) | F3(S) | F4(s)
| 0 | 0 | 0 | 0 | 0 | 0
| 1 | 0 | 4 | 6 | 6 | 6
| 2 | 0 | 7 | 10 | 11 | 11
| 3 | 0 | 9 | 13 | 15 | 15
| 4 | 0 | 12 | 15 | 19 | 19
| 5 | 0 | 15 | 18 | 22 | 23